## Hoja1
Nombre de la tarea | Responsables | Duración | Comienzo | Fin | 2018-01-28 | [5 empty] | 2018-02-04 | [5 empty] | 2018-02-11 | [5 empty] | 2018-02-18 | [5 empty] | 2018-02-25 | [5 empty] | 2018-03-04 | [5 empty] | 2018-03-11 | [5 empty] | 2018-03-18 | [5 empty] | 2018-03-25 | [5 empty] | 2018-04-01 | [5 empty] | 2018-04-09
[5 empty] | L | M | M | J | V | S | L | M | M | J | V | S | L | M | M | J | V | S | L | M | M | J | V | S | L | M | M | J | V | S | L | M | M | J | V | S | L | M | M | J | V | S | L | M | M | J | V | S | L | M | M | J | V | S | L | M | M | J | V | S | L | M | M | J | V | S
AVOINÉ |  | 82.25 days | jue 01/02/18 | sáb 07/04/18 | bar: 2018-01-28 J to 2018-04-01 S
Start |  | 0 days | jue 01/02/18 | jue 01/02/18 | bar: 2018-01-28 J
Planning |  | 12.38 days | jue 01/02/18 | vie 09/02/18 | bar: 2018-01-28 J to 2018-02-04 V
Meeting Minute | José Alfredo Armenta Blanco | 1 hour | jue 01/02/18 | jue 01/02/18 | bar: 2018-01-28 J
Life Cycle | José Alfredo Armenta Blanco | 1 hour | jue 01/02/18 | jue 01/02/18 | bar: 2018-01-28 J
Project Plan | Andrés Moreno García, José Alfredo Armenta Blanco, Laura Patricia Rangel Mora, Manuel Velázquez Martínez | 85 hours | vie 02/02/18 | vie 09/02/18 | bar: 2018-01-28 V to 2018-02-04 V
Release Meeting Minute Document, Project Plan |  | 0 days | vie 09/02/18 | vie 09/02/18
Analysis |  | 15.88 days | sáb 10/02/18 | mié 21/02/18 | bar: 2018-02-04 V to 2018-02-11 M
Meeting Minute | José Alfredo Armenta Blanco | 1 hour | vie 09/02/18 | vie 09/02/18 | bar: 2018-02-04 V
Requirements Management |  | 4.25 days | sáb 10/02/18 | mar 13/02/18 | bar: 2018-02-04 S to 2018-02-11 L
Evaluate the suppliers of requirements to interview | Laura Patricia Rangel Mora | 1 hour | sáb 10/02/18 | sab 10/02/18 | bar: 2018-02-04 S
Define the requirements collection | Laura Patricia Rangel Mora | 1 hour | sáb 10/02/18 | sab 10/02/18 | bar: 2018-02-04 S
Identify functional | Laura Patricia Rangel Mora | 4 hours | lun 12/02/18 | lun 12/02/18 | bar: 2018-02-11 L
Identify non-functional | Laura Patricia Rangel Mora | 4 hours | lun 12/02/18 | lun 12/02/18 | bar: 2018-02-11 M
Management |  | 4.38 days | lun 12/02/18 | jue 15/02/18 | bar: 2018-02-11 M to 2018-02-11 J
Prioritize the requirements | Laura Patricia Rangel Mora | 4 hours | lun 12/02/18 | lun 12/02/18 | bar: 2018-02-11 L
Assign the software requirements development group | Laura Patricia Rangel Mora | 4 hours | mar 13/02/18 | mar 13/02/18 | bar: 2018-02-11 M
Manage changes in requirements | Laura Patricia Rangel Mora | 4 hours | mié 14/02/18 | mié 14/02/18 | bar: 2018-02-11 M
Manage the traceability of the requirements | Laura Patricia Rangel Mora | 4 hours | jue 15/02/18 | jue 15/02/18 | bar: 2018-02-11 J
Requirements Management Document, Estrategy Requirements Management Document |  | 0 days | jue 15/02/18 | jue 15/02/18
Desing |  | 33.5 days | jue 15/02/18 | sáb 10/03/18 | bar: 2018-02-11 J to 2018-03-04 S
Meeting Minute | José Alfredo Armenta Blanco | 1 hour | jue 15/02/18 | jue 15/02/18 | bar: 2018-02-11 J
UML Diagrams |  | 12.38 days | jue 15/02/18 | vie 23/02/18 | bar: 2018-02-11 J to 2018-02-18 V
Use Cases Diagrams | Laura Patricia Rangel Mora | 18 hours | jue 15/02/18 | vie 16/02/18 | bar: 2018-02-11 J to 2018-02-11 V
Sequence Diagrams | Laura Patricia Rangel Mora | 18 hours | sáb 17/02/18 | lun 19/02/18 | bar: 2018-02-11 S to 2018-02-18 L
Class Diagrams | Laura Patricia Rangel Mora | 18 hours | lun 19/02/18 | mar 20/02/18 | bar: 2018-02-18 L to 2018-02-18 M
E-R Diagram | Laura Patricia Rangel Mora | 12 hours | jue 01/03/18 | jue 01/03/18 | bar: 2018-02-25 J
Relational Diagram | Laura Patricia Rangel Mora | 10 hours | vie 02/03/18 | vie 02/03/18 | bar: 2018-02-25 V
Layout | Laura Patricia Rangel Mora | 8 hours | sáb 03/03/18 | sáb 03/03/18 | bar: 2018-02-25 S
Navigation map | Laura Patricia Rangel Mora | 8 hours | lun 05/03/18 | lun 05/03/18 | bar: 2018-03-04 L
Logo | Laura Patricia Rangel Mora | 18 hours | lun 05/03/18 | mié 07/03/18 | bar: 2018-03-04 L to 2018-03-04 M
Website banner | Laura Patricia Rangel Mora | 18 hours | mié 07/03/18 | jue 08/03/18 | bar: 2018-03-04 M to 2018-03-04 J
Animations | Laura Patricia Rangel Mora | 18 hours | vie 09/03/18 | sáb 10/03/18 | bar: 2018-03-04 V to 2018-03-04 S
UML Diagrams Document, E-R Diagram, Relational Diagram , Loyaut, Navigation Map Document |  | 0 days | sáb 10/03/18 | sáb 10/03/18 | bar: 2018-03-04 S
Development |  | 25.75 days | sáb 10/03/18 | jue 05/04/18 | bar: 2018-03-04 S to 2018-04-01 J
Meeting Minute | José Alfredo Armenta Blanco | 1 hour | sáb 10/03/18 | sáb 10/03/18 | bar: 2018-03-04 S
Data Base Coding | Andrés Moreno García | 8 hours | sáb 10/03/18 | lun 12/03/18 | bar: 2018-03-04 S to 2018-03-11 L
Modules |  | 20.75 days | lun 12/03/18 | mar 03/04/18 | bar: 2018-03-11 L to 2018-04-01 M
Users |  | 3.75 days | lun 12/03/18 | mié 14/03/18 | bar: 2018-03-11 L to 2018-03-11 M
Interface | Manuel Velázquez Martínez | 6 hours | lun 12/03/18 | lun 12/03/18 | bar: 2018-03-11 L
List | Manuel Velázquez Martínez | 6 hours | lun 12/03/18 | mar 13/03/18 | bar: 2018-03-11 L to 2018-03-11 M
Register | Manuel Velázquez Martínez | 6 hours | mar 13/03/18 | mar 13/03/18 | bar: 2018-03-11 M
Delete | Manuel Velázquez Martínez | 6 hours | mar 13/03/18 | mié 14/03/18 | bar: 2018-03-11 M to 2018-03-11 M
Update | Manuel Velázquez Martínez | 6 hours | mié 14/03/18 | mié 14/03/18 | bar: 2018-03-11 M
LogIn |  | 1.5 days | mié 14/03/18 | jue 15/03/18 | bar: 2018-03-11 M to 2018-03-11 J
Interface | Manuel Velázquez Martínez | 6 hours | mié 14/03/18 | jue 15/03/18 | bar: 2018-03-11 M to 2018-03-11 J
User validation | Manuel Velázquez Martínez | 6 hours | jue 15/03/18 | jue 15/03/18 | bar: 2018-03-11 J
Publicity |  | 4 days | lun 19/03/18 | mié 21/03/18 | bar: 2018-03-18 L to 2018-03-18 M
Interface | Manuel Velázquez Martínez | 6 hours | lun 19/03/18 | lun 19/03/18 | bar: 2018-03-18 L
List | Manuel Velázquez Martínez | 6 hours | mar 20/03/18 | mar 20/03/18 | bar: 2018-03-18 M
Update | Manuel Velázquez Martínez | 6 hours | mié 21/03/18 | mié 21/03/18 | bar: 2018-03-18 M
Comments |  | 3.75 days | mié 21/03/18 | vie 23/03/18 | bar: 2018-03-18 M to 2018-03-18 V
Interface | Andrés Moreno García | 6 hours | mié 21/03/18 | mié 21/03/18 | bar: 2018-03-18 M
List | Andrés Moreno García | 6 hours | jue 22/03/18 | jue 22/03/18 | bar: 2018-03-18 J
Register | Andrés Moreno García | 6 hours | jue 22/03/18 | jue 22/03/18 | bar: 2018-03-18 J
Delete | Andrés Moreno García | 6 hours | jue 22/03/18 | vie 23/03/18 | bar: 2018-03-18 J to 2018-03-18 V
Update | Andrés Moreno García | 6 hours | vie 23/03/18 | vie 23/03/18 | bar: 2018-03-18 V
FAQ |  | 3.75 days | vie 23/03/18 | mar 03/04/18 | bar: 2018-03-18 V to 2018-04-01 M
Interface | Andrés Moreno García | 6 hours | vie 23/03/18 | sáb 24/03/18 | bar: 2018-03-18 V to 2018-03-18 S
List | Andrés Moreno García | 6 hours | sáb 24/03/18 | sáb 24/03/18 | bar: 2018-03-18 S
Register | Andrés Moreno García | 6 hours | sáb 24/03/18 | lun 02/04/18 | bar: 2018-03-18 S to 2018-03-25 L
Delete | Andrés Moreno García | 6 hours | lun 02/04/18 | lun 02/04/18 | bar: 2018-03-25 L
Update | Andrés Moreno García | 6 hours | lun 02/04/18 | mar 03/04/18 | bar: 2018-03-25 L to 2018-03-25 M
Meeting Minute | José Alfredo Armenta Blanco | 1 hour | mar 03/04/18 | mar 03/04/18 | bar: 2018-03-25 M
Test |  | 2.38 days | mié 04/04/18 | jue 05/04/18 | bar: 2018-03-25 M to 2018-03-25 J
Module Tests | Manuel Velázquez Martínez | 6 hours | mié 04/04/18 | mié 04/04/18 | bar: 2018-03-25 M
System Tests | Manuel Velázquez Martínez | 6 hours | jue 05/04/18 | jue 05/04/18 | bar: 2018-03-25 J
Test document |  | 0 days | jue 05/04/18 | jue 05/04/18 | bar: 2018-03-25 J
End of the project |  | 4.25 days | jue 05/04/18 | sáb 07/04/18 | bar: 2018-04-01 J to 2018-04-01 S
Letter of Acceptance | José Alfredo Armenta Blanco | 1 hour | jue 05/04/18 | jue 05/04/18 | bar: 2018-04-01 J
Project closure | José Alfredo Armenta Blanco | 1 hour | jue 05/04/18 | jue 05/04/18 | bar: 2018-04-01 J
Delivery of documentation and presentation | José Alfredo Armenta Blanco | 3 hours | jue 05/04/18 | jue 05/04/18 | bar: 2018-04-01 J
Final report |  | 0 days | sáb 07/04/18 | sáb 07/04/18 | bar: 2018-04-01 V
End of the project |  | 0 days | sáb 04/04/18 | sáb 07/04/18 | bar: 2018-04-01 V